## Synthetic Data Project Plan
ID | Original Text (Verbatim) | Action Plan | Status | Week | Deadline
Week 1: Jan 13 - Jan 17, 2026
3c | 3c. Sundar to get correct updated Schema (from repo) | PRIORITY #1 - Attack this first! Schema is mostly complete with 955 columns across 8 tables, but missing 11 columns preventing full validation: (1) fraud_verification: fraud_check_status, fraud_risk_score, income_verification_status, employment_verification_status, (2) credit_reports: inquiries_last_6mo_count, (3) payments: interest_accrued, snapshot_date, (4) Fix date type mismatches for SANITY-018, 019, (5) Resolve tradeline application_id datatype mismatch. Completing this will enable 59/60 checks (98.3% → 98.3%+) | Mostly Done/Under Review | 1 | 2026-01-17
3a | 3a. Move code / key documents to new GitHub repository | Repository created at github.com/sundar-bluesherpa/SynthDataProjCC with all validation reports, remediation code, and comprehensive documentation. Under review for completeness | Mostly Done/Under Review | 1 | 2026-01-17
3b | 3b. Rebuild / extract data consistency rules from existing code | Created 60 sanity checks (zero-tolerance) + 75+ comprehensive integrity checks across 9 validation categories. Under review to ensure all edge cases covered | Mostly Done/Under Review | 1 | 2026-01-17
Week 2: Jan 20 - Jan 24, 2026
3b2 | 3b2. Generate new data set with much larger number of records (target 1 million applications) | Generated 1,000,000 applications (20x target), 16.7M total rows across 8 tables with Gen 2 Markov state machine. Dataset validated at 98.0% pass rate, under review for final sign-off | Mostly Done/Under Review | 2 | 2026-01-24
3b3 | 3b3. Run existing code to test performance against large data set | Full 60-check validation suite runs successfully on 1M dataset in reasonable time with detailed violation reporting. Performance metrics under review | Mostly Done/Under Review | 2 | 2026-01-24
3e | 3e. Create expansive list of consistency rules across all attributes | 60 sanity checks implemented + 75+ integrity checks documented covering lifecycle, state machine, financial, temporal, credit bureau, fraud, and cross-table validations. Additional statistical validation checks being planned | Mostly Done/Under Review | 2 | 2026-01-24
Week 3: Jan 27 - Jan 31, 2026
3g | 3g. Create new code to generate data in alignment with these rules | Three-phase remediation completed: v1.0→v2.0→v3.0 achieving 98.0% pass rate with 99.5% violation reduction (1.2M→5,683 violations). Code under review for optimization opportunities | Mostly Done/Under Review | 3 | 2026-01-31
3h | 3h. Create validation code to check and diagnose created data | complete_sanity_validator_1M.py (60 checks) + extended_validation_suite.py (35+ checks) + comprehensive reporting with real data examples. Under review for additional diagnostic capabilities | Mostly Done/Under Review | 3 | 2026-01-31
2d.i | 2d.i. Additional integrity checks (note: original estimate was 2-3 days) | Fix remaining 11 skipped checks: Add missing columns (fraud_check_status, fraud_risk_score, income_verification_status, employment_verification_status, inquiries_last_6mo_count), fix date type comparisons, resolve tradeline join datatype mismatch. Target: 59/60 passing (98.3%) | Mostly Done/Under Review | 3 | 2026-01-31
Week 4: Feb 03 - Feb 07, 2026
3d | 3d. Generate proposed value ranges / distributions for each attribute | Create statistical validation suite: (1) Document expected ranges for all 955 columns, (2) Validate distributions (FICO: 640-850, interest: 6-25%, DTI, etc.), (3) Check correlations (FICO vs approval rate, DTI vs interest rate, credit score vs default), (4) Verify vintage distributions, (5) Add distribution tests to validation suite | PENDING | 4 | 2026-02-07
3f | 3f. Create strategy to create a dataset consistent with rules, ranges, distributions | Document generation strategy: (1) Review current Markov transition probabilities, (2) Validate Gaussian Copula correlations, (3) Document pricing curve logic, (4) Create strategy document for maintaining consistency at scale, (5) Add automated distribution checks to CI/CD pipeline | PENDING | 4 | 2026-02-07
Week 5: Feb 10 - Feb 14, 2026
3i | 3i. Brainstorm list of engineered features in data (fraud attack, new risk model, change in risk environment, new channel opens, etc.) | Design feature scenarios: (1) Fraud attack patterns (identity theft clusters, synthetic identity rings, bust-out schemes), (2) Risk model changes (FICO floor adjustment, DTI ceiling changes, approval rate shifts), (3) Environmental changes (recession impact, rate hikes, channel mix), (4) New channels (mobile app launch, partner integrations), (5) Document implementation approach for each | PENDING | 5 | 2026-02-14
3j | 3j. Develop strategy to implement features | Create feature implementation framework: (1) Design temporal injection points (by vintage/snapshot), (2) Create feature flags system in config.json, (3) Develop isolation strategy (separate feature validation), (4) Plan A/B testing scenarios, (5) Document rollback procedures, (6) Create feature metadata tracking | PENDING | 5 | 2026-02-14
Week 6: Feb 17 - Feb 21, 2026
3k | 3k. Update code/script to generate data set with features | Implement features in data_generator.py: (1) Add feature injection logic to Markov transitions, (2) Implement fraud pattern generators, (3) Add risk environment modifiers, (4) Create channel-specific behaviors, (5) Add feature tracking to output metadata, (6) Test feature isolation and interactions | PENDING | 6 | 2026-02-21
3l | 3l. Create code/script to validate features from the generated data | Build feature validation suite: (1) Create feature detection algorithms, (2) Validate fraud pattern recognition, (3) Verify risk model impact metrics, (4) Test channel attribution, (5) Add feature-specific sanity checks, (6) Create feature performance report generator, (7) Document expected vs actual feature metrics | PENDING | 6 | 2026-02-21
Week 7: Feb 24 - Feb 28, 2026
4 | 4. Next phase (ground truth development) | Plan ground truth framework: (1) Define ground truth requirements, (2) Design labeling strategy, (3) Create validation against known outcomes, (4) Plan model performance benchmarking approach, (5) Document ground truth maintenance procedures. Note: Detailed planning to begin after feature implementation complete | PENDING | 7 | 2026-02-28
PROJECT SUMMARY
Status Overview: | 8 tasks Mostly Done/Under Review, 6 tasks Pending
PRIORITY #1: | 3c - Complete schema (11 missing columns) - ATTACK THIS FIRST
Weeks 1-3: | Under Review - Validation framework & 1M dataset generation (98.0% pass rate achieved)
Week 4: | Statistical validation & distribution analysis
Weeks 5-6: | Feature engineering design & implementation
Week 7: | Ground truth planning
Current Achievement: | 98.0% validation pass rate (48/49 checks), 11 checks skipped due to missing columns
Dataset Scale: | 1M applications, 16.7M total rows
Repository: | github.com/sundar-bluesherpa/SynthDataProjCC